From the desk of Scott…..

Date:  May 24, 2018

To: Wayne / Bryce

Regarding: UPC Plan

UPC is now on a timeline.  It needs to become profitable or that clinic will need to be shut down.  I have set up a timeline and goals that need to be reached.  Currently the timeline has a deadline date of beginning of Sept but once we get the lease info back from the landlord, I would be able to confirm the actual dates.  I have broken the main plan up into 3 sections.  Section 1 focuses on establishing control on expenses, promoting, and implementing a proper chain of command.  Section 2 has a focus of increase sales and maintain responsible spending and section 3 is focused on improving what we have established as “working improvements”  Each section also has a time frame and an important point to remember is that if the targets fall behind the decision to close down UPC may be moved up.

Expectations

Below is the plan for section 1 and should begin immediately.  The obvious expectation is that any task that has been assigned to you will be completed ASAP due to the short timeframe to begin with.  As what we have discussed in the past, the expectation isn’t that you complete these tasks on your own but instead you use whatever team members are available and are capable of completing the work.  The expectation is that the tasks that are completed have been supervised by you and you satisfied with the work.  Basically, you are not responsible to complete all the tasks yourself but you are responsible for the how the task was completed.  I would also expect to be updated regularly with the status of the plan.

I have left room on the plan for any other ideas that you would want to include.  I would expect to see additional tasks added by you that line up with the focus of the section

UPC PLAN – SECTION 1

May 23 – June 13

FOCUS

- Minimizing expenses where possible

- Manage team to create more accountability and more efficiency

- Improve clinic exposure and promote clinic

- Track daily sales from May 21/18

| TASK TO | TASK | STATUS/COMMENTS |
| --- | --- | --- |
| Bryce | Work at decreasing expenses wherever possible |  |
| Bryce | Ensure all expenses are approved by you before any money is spent |  |
| Bryce | Increase number of clients that call the clinic – begin tracking |  |
| Wayne | Increase the number of clients that enter the building – begin tracking |  |
| Wayne | Increase the number of patient that enter the building Begin tracking |  |
| Wayne | Increase the number of traffic we get on the UPC website Begin tracking |  |
| Bryce | Manage team – set up clinic manager. Ensure roles and expectations are clear as per org chart |  |
| Bryce | Manage team – create and implement a “refer or defer” OG complete with any needed administrative paperwork |  |
| Bryce | Manage team – create and implement an end of day summary – this will help with tracking item from above |  |
| Bryce | Track daily sales and running average as of May 21/18 |  |
| Scott | Set up GOALS for this period and review plan and goals with management team |  |
|  | Any other ideas………………. |  |

June 13 – July 18

Increase clients

Increase per avg transaction

Watch expenses

July 18 – Aug 18

Continuie with managing team

Continue with increasing number of clients

Continue to work on improving compliance

Aug 30 – If sales have not reached their target move to phase 2 which ois to close the doors