# 500 Day Plan

Background and Overview

Purpose of the 500 Day Plan

The clinics have reached a point where financial clarity and operational focus are necessary to ensure long-term stability.

While the clinics continue to provide excellent care to patients and clients, the financial performance of the organization has not consistently produced the level of profitability required to support long-term stability.

The purpose of the 500 Day Plan is to create a structured and measurable path toward stronger financial performance while maintaining the quality of care that defines the clinics.

The 500 Day Timeline

Preparation Period: March 5 – March 14, 2026

Plan Start Date: March 15, 2026

Plan Completion: July 28, 2027

Total Duration: 500 Days

Leadership will review progress every 37 days to ensure the plan remains on track and to make adjustments when necessary.

Current Financial Reality

Estimated annual sales across the clinics are approximately $7,000,000.

Current net profit is estimated at approximately 10%, producing roughly $700,000 in annual operating profit.

This level of profitability supports normal clinic operations but does not create sufficient financial capacity to strengthen the long‑term financial position of the organization.

Baseline Operating Profit

The current profit level of approximately 10% is considered the baseline operating profit required to maintain normal clinic operations including staffing, facilities, equipment, medical supplies, and general business operations.

Business Recovery Target

The objective of the 500 Day Plan is to generate:

Business Recovery Target: $888,888 in new profit over 500 days.

This recovery profit must be generated in addition to the baseline 10% operating profit.

Required Profit Improvement

To achieve the recovery target within 500 days, the clinics must generate approximately $650,000 in additional annual profit.

This would move the clinics from approximately 10% profitability to roughly 19% profitability.

Veterinary practices operating at strong financial performance commonly operate within the 18–22% profit range, making this target realistic and achievable.

Daily Progress Target

To reach the business recovery target within 500 days the clinics must generate:

$1,777 in new profit per day.

This represents profit created above the baseline operating level.

37 Day Performance Cycles

The 500 Day Plan operates in 37‑day performance cycles.

At each checkpoint leadership will review:

• financial performance

• operational improvements

• areas requiring adjustment

Expected progress per 37‑day cycle:

$65,777 in new profit.

The Cost of Doing Nothing

If the clinics continue operating at their current level of performance, the organization will likely remain near 10% profitability.

While this level of performance supports basic operations, it does not provide the financial strength required to create long‑term stability or financial flexibility.

A Framework for Improvement

The 500 Day Plan provides one structured framework for improving financial performance.

The purpose of the plan is not to prescribe a single solution but to establish clear financial targets and measurable progress.

If alternative strategies are identified that can achieve the same financial outcome within the same timeframe, those ideas should absolutely be considered.

The 500 Day Question

The question is not whether improvement is possible — the initial analysis suggests that it is.

The real question is whether we choose to pursue the opportunity in a structured and disciplined way over the next 500 days.

Improvement Framework (Overview)

The framework looks at five primary areas where operational improvement may exist across the clinics.

1. COGS Discipline

Improving purchasing controls, inventory management, and supplier price alignment.

2. Labour Alignment

Ensuring labour hours and roles are aligned with actual clinic demand.

3. Value Creation / Per Average Transaction (PAT) Improvement

Small pricing adjustments, improved service capture, and reduction of missed charges.

4. Operational Expansion

Improved utilization of existing facilities such as evening urgent care services.

5. Variable Cost Review

Review of discretionary expenses that may have grown over time without regular evaluation.

Each area represents a category of initiatives that can be implemented individually or in combination depending on leadership priorities.

Opportunity Map (High-Level Estimate)

Estimated Profit Opportunities Identified

COGS Discipline: approximately $120,000

Labour Alignment: approximately $150,000

PAT / Pricing Improvements: approximately $460,000

UPC Expansion: approximately $65,000

Variable Cost Review: approximately $15,000

Interest Reduction (cash flow improvement): up to $50,000

Total Opportunity Identified: approximately $860,000

Target Required: approximately $650,000

Buffer: approximately $210,000

This map illustrates that the required improvement may be achievable through a combination of smaller operational adjustments rather than relying on a single major change.